## Sheet1 (2)
ATE#ID | ATE PC Name | Motherboard | Location | Configuration | Status | Updates | Microsoft License | Ackermann License | SSD Serial Number |  | Remarks
[9 empty] | SN#1 | SN#2
1 | ATE1-0301011 |  | Test Services | 480V | Done | Done | 9QP2F-7NGXJ-4CJ64-MCP3G-BP49D | AMPR0-C0X00-G1H1J-K8N12-3M3IS-ZEDCK-B42C | S74ZNX0Y308506 | S74ZNX0Y828974
2 | ATE2-SN2112003 | X10SAE | Texon-1 (Gumi) | ? | On Progress | Shipped (18 Dec 25) Delivered (2 Jan 26) Delivery Confirmed (5 Jan 26) -> On Progress Installation (Lee Daeyong - Texon KR) | H7QYP-NTTFC-V3MTM-DPMFV-G6R9D |  | S74ZNX0Y828980A | S74ZNX0Y308510J
3 | ATE3-2112006 | Advantech | Texon-2 (Gumi) | 480V | On Progress |  | YXC72-NKRPV-BTVRB-HJ83J-TRBP3 |  | S74ZNX0Y827272V | S74ZNX0Y308518E
4 | ATE4-2109004 | Advantech | Texon-3 (Gumi) | 480V | On Progress |  | V9YR8-7WNBB-PYF2W-WJGXX-KQFC3 |  | S74ZNX0Y828988D | S74ZNX0Y912879F
5 | ATE5-2112005 | Advantech | Texon-4 (Gumi) | 480V | On Progress |  | GNDCW-JPG37-R7FFT-HXJHR-KBXTQ |  | S74ZNX0Y828973W | S74ZNX0Y809031D
6 | ATE6-2201008 | Advantech | Texon-5 (Gumi) | 480V | On Progress |  | GN27K-4YKF6-7G9WQ-M9JPY-KFBP3 |  | S74ZNX0Y828978Z | S74ZNX0Y809033V
7 | ATE7-2201007 | Advantech | Texon-6 (Vietnam) | 480V | On Progress | Waiting for Delivery Address | X23WN-T8XQF-9HK6D-K26K4-PPT6Q |  | S74ZNX0Y308516F | S74ZNX0Y809038Y
8 | ATE8-SN2112010 | X10SAE | Jabil-1 (Penang) | ? | On Progress | Shipped (18 Dec 25) Delivered (19 Dec 25) -> Waiting for delivery confirmation to start the installation (Boonkuan - Jabil) | MQW9N-BY4JG-K64JX-KFQVC-FYCKD |  | S74ZNX0Y308519T | S74ZNX0Y809032R
9 | ATE9-SN2112004 | X10SAE | Jabil-2 (Penang) | ? | On Progress |  | CN8WM-PHK66-PF47V-YVMWF-7H9TQ |  | S74ZNX0Y308515K | S74ZNX0Y809028T
10 | ATE10-2202009 | Advantech | Jabil-3 (Penang) | 480V | On Progress |  | QQM3N-WWK73-HF4GD-JY869-V249D |  | S74ZNX0Y308509X | S74ZNX0Y809035X
11 | ATE11-2205010 | Advantech | Jabil-4 (Penang) | 480V | On Progress |  | YRM6J-NHY2T-2FHMF-BX84X-6CT6Q |  | S74ZNX0Y913009A | S74ZNX0Y311036D
12 | ATE12-2011001 | Advantech | Avalon-1 | 480V | Done (9 Jan 26) | Shipped (19 Dec 25) Delivered (26 Dec 25) Delivery Confirmed (29 Dec 25) Done Installation (9 Jan 26) | 8TBH9-4NQG6-F4FFG-4DDMQ-YBMP3 | AMPS0-90E00-G1H1J-K8N1Q-3J3G9-FFXMQ-8QMR | S74ZNX0Y913010Y | S74ZNX0Y308636P
13 | ATE13-2302014 | Advantech | Cyient-1 | 480V | Done (6 Jan 26) | Shipped (19 Dec 25) Delivered (20 Dec 25) Delivery Confirmed (26 Dec 25) Done Installation (6 Jan 26) | VM22P-D7NCG-6FT6G-CHWMF-YTG6Q | AMPP0-R0400-G1H1J-K8N1I-3T337-YGYWA-NWYN | S74ZNX0Y913014V | S74ZNX0Y308522A
14 | ATE14-2106003 | Advantech | Plexus-1 |  | On Progress | Shipped (19 Dec 25) Delivered (29 Dec 25) Delivery Confirmed (5 Jan 26) -> On Progress Installation (Nazura - Plexus) | B3NYW-7YB8C-M3BTP-9VD3Y-JMCKD |  | S74ZNX0Y913012B | S74ZNX0Y311035V
15 | ATE15-2301012 | Advantech | Plexus-2 |  | On Progress |  | WQYFN-B4XKG-6YMP6-BJQDH-MBMP3 |  | S74ZNX0Y809029A | S74ZNX0Y311009B
16 | ATE16-2302013 | Advantech | Plexus-3 |  | Done (13 Jan 26) |  | FN94B-4TPH8-V38V8-W4T77-YY8XD |  | S74ZNX0Υ809027J | S75BNL0X906465D
17 | ATE17-2011002 | Advantech | UCAP-1 |  | Done (12 Jan 26) | Done Installation (12 Jan 26) | DTTNK-TFXK9-WB6R6-G9V3W-YP49D |  | S74ZNX0Y912881L | S75BNL0X906458V
18 | ATE18-SN2112015 | Advantech | Celestica-1 |  | On Progress | Shipped (19 Dec 25) Delivered (22 Dec 25) Delivery Confirmed (29 Dec 25) -> Waiting for delivery confirmation to start the installation (Zaki - Celestica) | VMNCY-JWP8Q-F33GV-8YF74-9W66Q |  | S74ZNX0Y912882D | S75BNL0X906481Z
19 | ATE19- | - | Jabil-5 (Guad) |  | On Progress | Waiting for System Information Feedback | VDHT4-J2NJB-KCXR9-HK22P-9QFC3 |  | S74ZNX0Y913011R | S75BNL0X906466M
20 | ATE20- | - | Jabil-6 (Guad) |  | On Progress |  | TJN6D-Y8VKY-J964P-HB6QX-MHDGQ |  | S74ZNX0Y912880E | S74ZNX0Y311025P
21 | ATE21-SN2112014 | Advantech | Smantek-1 | 208V | On Progress | Waiting for Delivery Address | NCT8T-FFCMK-QH4RH-3TWDV-3J66Q |  | S74ZNΧ0Υ809036H | S74ZNX0Y311037W
22 | ATE22-SN2112016 | Asus | Texon-7 (US) |  | On Progress | Waiting for Delivery Address | RNVCT-P43B3-JV9RX-MF63D-KK3GQ |  | S74ZNΧ0Υ809034Z | S74ZNX0Y311027A
23 | ATE23-SN2112008 | Advantech | Test Services | 480V | On Progress | -> For TS Inhouse upgrade |  | AMPG0-N0K00-G1H1J-K8N1I-3H34D-HHX9Y-78GU | S74ZNΧ0Υ913008 | S74ZNX0Y311034
24 | ATE24-SN2112011 | Advantech | Avalon-2 | 208V | Done | Done | WBNKH-GC9RD-F3CM9-DTPQG-FVYP3 | AMPH0-T0400-G1H1J-K8N1Y-333CC-XFRAA-X2HN | S74ZNX0Y823254Z | S74ZNX0Y838778L
25 | ATE25-SN2112012 | Advantech | Cyient-2 | 480V | Done | Done | MNKBX-VVCK7-6HYRJ-FMHM7-RGG6Q | AMPD0-70F00-G1H1J-K8N1S-3Y3Q3-4AXTU-SJCX | S74ZNX0Y817266 | S74ZNXOY823209
26 | ATE26-2603015 | Advantech | Texon-8 (Gumi) |  | Done | Done |  | AMPA0-P0V00-G1H1J-K8N17-3J3FE-KBZYK-YXNN | S6P5NS0YA02244L | S6P5NS0YA02237X
27
28 | ATE28-2605016 | Advantech | Texon-8 (Gumi) |  |  |  | TG8QT-MNTR6-BMDRW-PVYM6-4M8XH | AMPM0-R0J00-G1H1J-K8N1T-363E7-AQNIS-VWHG | 2Q0929A6QDWF | 2Q032L2NDBHY
29 | ATE29-1707017 | [5 empty] | VB97N-T6RWC-XQDVX-FW9V9-T866Q
[8 empty] | AMPD0-E0B00-G1H2J-K8N18-3K3VE-2AJGS-S8SC |  |  | For LAM PC Only